## Index
The PMI Project Management Standard
| 1 | Index | Version Control and References
| 2 | Knowledge Areas | Processes organized by knowledge areas and process group
| 3 | Process Group | Processes organized by process group
| 4 | Processes | Processes and its inputs, outputs and tools (5th Edition)
| 5 | Parameters | Parameters
References
Ref. | Reference
1 | PROJECT MANAGEMENT INSTITUTE. A Guide to the Project Management Body of Knowledge (PMBOK® Guide). Pennsylvania: PMI, 2013.
2 | PMI - PROJECT MANAGEMENT INSTITUTE. ExposureDraft – PMBOK ® Guide Sixth Edition (Front End and Knowledge Area Sections), Pennsylvania: PMI, 2017.
3
Version Control
Version | Date | Author | Review Notes
1.0 | 2017-05-17 | Eduardo Montes, PMP | Draft of the ExposureDraft - PMBOK® Sixth Edition

## KnowledgeAreas
Cod. | Process 6th Edition | Knowledge Areas | Process Group | Link to Portuguese explanation | PMBOK 5th Edition | Type of change | Change | Check
4.1 | Develop Project Charter | 4 - Integration | Initiating | Develop Project Charter | 4.1
4.2 | Develop Project Management Plan | 4 - Integration | Planning | Develop Project Management Plan | 4.2
4.3 | Direct and Manage Project Work | 4 - Integration | Executing | Direct and Manage Project Work | 4.3
4.4 | Manage Project Knowledge | 4 - Integration | Executing |  |  | New process | New process | 1
4.5 | Monitor and Control Project Work | 4 - Integration | Monitoring & Controlling | Monitor and Control Project Work | 4.4
4.6 | Perform Integrated Change Control | 4 - Integration | Monitoring & Controlling | Perform Integrated Change Control | 4.5
4.7 | Close Project or Phase | 4 - Integration | Closing | Close Project or Phase | 4.6
5.1 | Plan Scope Management | 5 - Scope | Planning | Plan Scope Management | 5.1
5.2 | Collect Requirements | 5 - Scope | Planning | Collect Requirements | 5.2
5.3 | Define Scope | 5 - Scope | Planning | Define Scope | 5.3
5.4 | Create WBS | 5 - Scope | Planning | Create WBS | 5.4
5.5 | Validate Scope | 5 - Scope | Monitoring & Controlling | Validate Scope | 5.5
5.6 | Control Scope | 5 - Scope | Monitoring & Controlling | Control Scope | 5.6
6.1 | Plan Schedule Management | 6 - Time | Planning | Plan Schedule Management | 6.1
6.2 | Define Activities | 6 - Time | Planning | Define Activities | 6.2
6.3 | Sequence Activities | 6 - Time | Planning | Sequence Activities | 6.3
6.4 | Estimate Activity Durations | 6 - Time | Planning | Estimate Activity Durations | 6.5
6.5 | Develop Schedule | 6 - Time | Planning | Develop Schedule | 6.6
6.6 | Control Schedule | 6 - Time | Monitoring & Controlling | Control Schedule | 6.7
7.1 | Plan Cost Management | 7 - Cost | Planning | Plan Cost Management | 7.1
7.2 | Estimate Costs | 7 - Cost | Planning | Estimate Costs | 7.2
7.3 | Determine Budget | 7 - Cost | Planning | Determine Budget | 7.3
7.4 | Control Costs | 7 - Cost | Monitoring & Controlling | Control Costs | 7.4
8.1 | Plan Quality Management | 8 - Quality | Planning | Plan Quality Management | 8.1
8.2 | Manage Quality | 8 - Quality | Executing | Perform Quality Assurance | Perform Quality Assurance | Changed name | From Perform Quality Assurance to Manage Quality | 1
8.3 | Control Quality | 8 - Quality | Monitoring & Controlling | Control Quality | 8.3
9.1 | Plan Resource Management | 9 - Resource | Planning | Plan Human Resource Management | Plan Human Resource Management | Changed name | From Human Resource to Resource | 1
9.2 | Estimate Activity Resources | 9 - Resource | Planning | Estimate Activity Resources | 6.4 | Moved | Moved from Time to Resource | 1
9.3 | Acquire Resources | 9 - Resource | Executing | Acquire Project Team | Acquire Project Team | Changed name | From Project Team to Resources | 1
9.4 | Develop Team | 9 - Resource | Executing | Develop Project Team | Develop Project Team | Changed name | From Project Team to Team | 1
9.5 | Manage Team | 9 - Resource | Executing | Manage Project Team | Manage Project Team | Changed name | From Project Team to Team | 1
9.6 | Control Resources | 9 - Resource | Monitoring & Controlling |  |  | New process | New process | 1
10.1 | Plan Communications Management | 10 - Communications | Planning | Plan Communications Management | 10.1
10.2 | Manage Communications | 10 - Communications | Executing | Manage Communications | 10.2
10.3 | Monitor Communications | 10 - Communications | Monitoring & Controlling | Control Communications | Control Communications | Changed name | From Control to Monitor | 1
11.1 | Plan Risk Management | 11 - Risk | Planning | Plan Risk Management | 11.1
11.2 | Identify Risks | 11 - Risk | Planning | Identify Risks | 11.2
11.3 | Perform Qualitative Risk Analysis | 11 - Risk | Planning | Perform Qualitative Risk Analysis | 11.3
11.4 | Perform Quantitative Risk Analysis | 11 - Risk | Planning | Perform Quantitative Risk Analysis | 11.4
11.5 | Plan Risk Responses | 11 - Risk | Planning | Plan Risk Responses | 11.5
11.6 | Implement Risk Responses | 11 - Risk | Executing |  |  | New process | New process | 1
11.7 | Monitor Risks | 11 - Risk | Monitoring & Controlling | Control Risks | Control Risks | Changed name | From Control to Monitor | 1
12.1 | Plan Procurement Management | 12 - Procurement | Planning | Plan Procurement Management | 12.1
12.2 | Conduct Procurements | 12 - Procurement | Executing | Conduct Procurements | 12.2
12.3 | Control Procurements | 12 - Procurement | Monitoring & Controlling | Control Procurements | 12.3
13.1 | Identify Stakeholders | 13 - Stakeholder | Initiating | Identify Stakeholders | 13.1
13.2 | Plan Stakeholder Engagement | 13 - Stakeholder | Planning | Plan Stakeholder Management | Plan Stakeholder Management | Changed name | From Management to Engagement
13.3 | Manage Stakeholder Engagement | 13 - Stakeholder | Executing | Manage Stakeholder Engagement | 13.3
13.4 | Monitor Stakeholder Engagement | 13 - Stakeholder | Monitoring & Controlling | Control Stakeholder Engagement | Control Stakeholder Engagement | Changed name | From Control to Monitor | 1
|  | 12 - Procurement | Closing | Close Procurements | Close Procurements | Process removed | Removed

## ProcessGroup
Knowledge Areas | Initiating | Planning | Executing | Monitoring & Controlling | Closing
4. Integration | Develop Project Charter | Develop Project Management Plan | Direct and Manage Project Work | Monitor and Control Project Work | Close Project or Phase
|  |  | Manage Project Knowledge | Perform Integrated Change Control
5. Scope |  | Plan Scope Management |  | Validate Scope
|  | Collect Requirements |  | Control Scope
Define Scope
Create WBS
6. Time |  | Plan Schedule Management |  | Control Schedule
Define Activities
Sequence Activities
Estimate Activity Durations
Develop Schedule
7. Cost |  | Plan Cost Management |  | Control Costs
Estimate Costs
Determine Budget
8. Quality |  | Plan Quality Management | Manage Quality | Control Quality
9. Human Resource |  | Plan Resource Management | Acquire Resources | Control Resources
|  | Estimate Activity Resources | Develop Team
Manage Team
10. Communications |  | Plan Communications Management | Manage Communications | Monitor Communications
11. Risk |  | Plan Risk Management | Implement Risk Responses | Monitor Risks
Identify Risks
Perform Qualitative Risk Analysis
Perform Quantitative Risk Analysis
Plan Risk Responses
12. Procurement |  | Plan Procurement Management | Conduct Procurements | Control Procurements
13. Stakeholder | Identify Stakeholders | Plan Stakeholder Engagement | Manage Stakeholder Engagement | Monitor Stakeholder Engagement
| 2 | 24 | 10 | 12 | 1

## Processes
Seq. | Cod. | Process | Ref. | Input ¦ Tools & Techniques ¦ Output | Tipo | Group | Edition | Change | Previous or Incorporated into
1 | 4.1 | Develop Project Charter | 0 | Project statement of work | Input | Initiating | 6 | Removed
2 | 4.1 | Develop Project Charter | 1 | Business documents | Input | Initiating | 6 | Broader | Business case
3 | 4.1 | Develop Project Charter | 2 | Agreements | Input | Initiating | 6 | No
4 | 4.1 | Develop Project Charter | 3 | Enterprise environmental factors | Input | Initiating | 6 | No
5 | 4.1 | Develop Project Charter | 4 | Organizational process assets | Input | Initiating | 6 | No
6 | 4.1 | Develop Project Charter | 1 | Expert judgement | Tools | Initiating | 6 | No
6 | 4.1 | Develop Project Charter | 2 | Data gathering | Tools | Initiating | 6 | Added
7 | 4.1 | Develop Project Charter | 3 | Interpersonal and team skills | Tools | Initiating | 6 | Broader | Facilitation techniques
8 | 4.1 | Develop Project Charter | 1 | Project charter | Output | Initiating | 6 | No
8 | 4.1 | Develop Project Charter | 2 | Assumption log | Output | Initiating | 6 | Added
9 | 4.2 | Develop Project Management Plan | 1 | Project charter | Input | Planning | 6 | No
10 | 4.2 | Develop Project Management Plan | 2 | Outputs from other processes | Input | Planning | 6 | No
11 | 4.2 | Develop Project Management Plan | 3 | Enterprise environmental factors | Input | Planning | 6 | No
12 | 4.2 | Develop Project Management Plan | 4 | Organizational process assets | Input | Planning | 6 | No
13 | 4.2 | Develop Project Management Plan | 1 | Expert judgement | Tools | Planning | 6 | No
13 | 4.2 | Develop Project Management Plan | 2 | Data gathering | Tools | Planning | 6 | Added
14 | 4.2 | Develop Project Management Plan | 3 | Interpersonal and team skills | Tools | Planning | 6 | Broader | Facilitation techniques
14 | 4.2 | Develop Project Management Plan | 4 | Meetings | Tools | Planning | 6 | Added
15 | 4.2 | Develop Project Management Plan | 1 | Project management plan | Output | Planning | 6 | No
16 | 4.3 | Direct and Manage Project Work | 1 | Project management plan | Input | Executing | 6 | No
16 | 4.3 | Direct and Manage Project Work | 2 | Project documents | Input | Executing | 6 | Added
17 | 4.3 | Direct and Manage Project Work | 3 | Approved change requests | Input | Executing | 6 | No
18 | 4.3 | Direct and Manage Project Work | 4 | Enterprise environmental factors | Input | Executing | 6 | No
19 | 4.3 | Direct and Manage Project Work | 5 | Organizational process assets | Input | Executing | 6 | No
20 | 4.3 | Direct and Manage Project Work | 1 | Expert judgement | Tools | Executing | 6 | No
21 | 4.3 | Direct and Manage Project Work | 2 | Project management information system | Tools | Executing | 6 | No
22 | 4.3 | Direct and Manage Project Work | 3 | Meetings | Tools | Executing | 6 | No
23 | 4.3 | Direct and Manage Project Work | 1 | Deliverables | Output | Executing | 6 | No
24 | 4.3 | Direct and Manage Project Work | 2 | Work performance data | Output | Executing | 6 | Narrower | Work performance information
24 | 4.3 | Direct and Manage Project Work | 3 | Issue log | Output | Executing | 6 | Added
25 | 4.3 | Direct and Manage Project Work | 4 | Change requests | Output | Executing | 6 | No
26 | 4.3 | Direct and Manage Project Work | 5 | Project management plan updates | Output | Executing | 6 | No
27 | 4.3 | Direct and Manage Project Work | 6 | Project documents updates | Output | Executing | 6 | No
27 | 4.3 | Direct and Manage Project Work | 7 | Organizational process assets updates | Output | Executing | 6 | Added
| 4.4 | Manage project knowledge | 1 | Project management plan | Input | Executing | 6
| 4.4 | Manage project knowledge | 2 | Project documents | Input | Executing | 6
| 4.4 | Manage project knowledge | 3 | Deliverables | Input | Executing | 6
| 4.4 | Manage project knowledge | 4 | Enterprise environmental factors | Input | Executing | 6
| 4.4 | Manage project knowledge | 5 | Organizational process assets | Input | Executing | 6
| 4.4 | Manage project knowledge | 1 | Expert judgement | Tools | Executing | 6
| 4.4 | Manage project knowledge | 2 | Knowledge management | Tools | Executing | 6 | Added
| 4.4 | Manage project knowledge | 3 | Information management | Tools | Executing | 6 | Added
| 4.4 | Manage project knowledge | 4 | Interpersonal and team skills | Tools | Executing | 6 | Added
| 4.4 | Manage project knowledge | 1 | Lessons learned register | Output | Executing | 6 | Added
| 4.4 | Manage project knowledge | 2 | Project management plan updates | Output | Executing | 6
| 4.4 | Manage project knowledge | 3 | Organizational process assets updates | Output | Executing | 6
28 | 4.4 | Monitor and Control Project Work | 1 | Project management plan | Input | Controling | 6 | No
29 | 4.4 | Monitor and Control Project Work | 2 | Project documents | Input | Controling | 6 | Broader | Schedule forecasts
30 | 4.4 | Monitor and Control Project Work | 0 | Cost forecasts | Input | Controling | 6 | Incorporated into | Project documents
31 | 4.4 | Monitor and Control Project Work | 0 | Validated changes | Input | Controling | 6 | Removed
32 | 4.4 | Monitor and Control Project Work | 3 | Work performance information | Input | Controling | 6 | No
32 | 4.4 | Monitor and Control Project Work | 4 | Agreements | Input | Controling | 6 | Added
33 | 4.4 | Monitor and Control Project Work | 5 | Enterprise environmental factors | Input | Controling | 6 | No
34 | 4.4 | Monitor and Control Project Work | 6 | Organizational process assets | Input | Controling | 6 | No
35 | 4.4 | Monitor and Control Project Work | 1 | Expert judgement | Tools | Controling | 6 | No
36 | 4.4 | Monitor and Control Project Work | 2 | Data analysis | Tools | Controling | 6 | Broader | Analytical techniques
36 | 4.4 | Monitor and Control Project Work | 3 | Decision making | Tools | Controling | 6 | Added
37 | 4.4 | Monitor and Control Project Work | 0 | Project management information system | Tools | Controling | 6 | Removed
38 | 4.4 | Monitor and Control Project Work | 4 | Meetings | Tools | Controling | 6 | No
39 | 4.4 | Monitor and Control Project Work | 2 | Change requests | Output | Controling | 6 | No
40 | 4.4 | Monitor and Control Project Work | 1 | Work performance reports | Output | Controling | 6 | No
41 | 4.4 | Monitor and Control Project Work | 3 | Project management plan updates | Output | Controling | 6 | No
42 | 4.4 | Monitor and Control Project Work | 4 | Project documents updates | Output | Controling | 6 | No
43 | 4.5 | Perform Integrated Change Control | 1 | Project management plan | Input | Controling | 6 | No
43 | 4.5 | Perform Integrated Change Control | 2 | Project documents | Input | Controling | 6 | Added
44 | 4.5 | Perform Integrated Change Control | 3 | Work performance reports | Input | Controling | 6 | No
45 | 4.5 | Perform Integrated Change Control | 4 | Change requests | Input | Controling | 6 | No
46 | 4.5 | Perform Integrated Change Control | 5 | Enterprise environmental factors | Input | Controling | 6 | No
47 | 4.5 | Perform Integrated Change Control | 6 | Organizational process assets | Input | Controling | 6 | No
48 | 4.5 | Perform Integrated Change Control | 1 | Expert judgement | Tools | Controling | 6 | No
48 | 4.5 | Perform Integrated Change Control | 3 | Data analysis | Tools | Controling | 6 | No
48 | 4.5 | Perform Integrated Change Control | 4 | Decision making | Tools | Controling | 6 | No
49 | 4.5 | Perform Integrated Change Control | 5 | Meetings | Tools | Controling | 6 | No
50 | 4.5 | Perform Integrated Change Control | 2 | Change control tools | Tools | Controling | 6 | No
51 | 4.5 | Perform Integrated Change Control | 1 | Approved change requests | Output | Controling | 6 | No
52 | 4.5 | Perform Integrated Change Control | 0 | Change log | Output | Controling | 6 | Incorporated into | Project documents
53 | 4.5 | Perform Integrated Change Control | 2 | Project management plan updates | Output | Controling | 6 | No
54 | 4.5 | Perform Integrated Change Control | 3 | Project documents updates | Output | Controling | 6 | No
55 | 4.6 | Close Project or Phase | 1 | Project charter | Input | Closing | 6 | Added
55 | 4.6 | Close Project or Phase | 2 | Project management plan | Input | Closing | 6 | No
55 | 4.6 | Close Project or Phase | 3 | Project documents | Input | Closing | 6 | Added
56 | 4.6 | Close Project or Phase | 4 | Accepted deliverables | Input | Closing | 6 | No
56 | 4.6 | Close Project or Phase | 5 | Business documents | Input | Closing | 6 | Added
56 | 4.6 | Close Project or Phase | 6 | Agreements | Input | Closing | 6 | Added
56 | 4.6 | Close Project or Phase | 7 | Procurement documentation | Input | Closing | 6 | Added
57 | 4.6 | Close Project or Phase | 8 | Organizational process assets | Input | Closing | 6 | No
58 | 4.6 | Close Project or Phase | 1 | Expert judgement | Tools | Closing | 6 | No
59 | 4.6 | Close Project or Phase | 2 | Data analysis | Tools | Closing | 6 | Broader | Analytical techniques
60 | 4.6 | Close Project or Phase | 3 | Meetings | Tools | Closing | 6 | No
61 | 4.6 | Close Project or Phase | 1 | Final product, service, or result transition | Output | Closing | 6 | No
61 | 4.6 | Close Project or Phase | 2 | Project documents updates | Output | Closing | 6 | Added
62 | 4.6 | Close Project or Phase | 3 | Organizational process assets updates | Output | Closing | 6 | No
63 | 5.1 | Plan Scope Management | 2 | Project management plan | Input | Planning | 6 | No
64 | 5.1 | Plan Scope Management | 1 | Project charter | Input | Planning | 6 | No
65 | 5.1 | Plan Scope Management | 3 | Enterprise environmental factors | Input | Planning | 6 | No
66 | 5.1 | Plan Scope Management | 4 | Organizational process assets | Input | Planning | 6 | No
67 | 5.1 | Plan Scope Management | 1 | Expert judgement | Tools | Planning | 6 | No
67 | 5.1 | Plan Scope Management | 2 | Data analysis | Tools | Planning | 6 | Added
68 | 5.1 | Plan Scope Management | 3 | Meetings | Tools | Planning | 6 | No
69 | 5.1 | Plan Scope Management | 1 | Scope management plan | Output | Planning | 6 | No
70 | 5.1 | Plan Scope Management | 2 | Requirements management plan | Output | Planning | 6 | No
71 | 5.2 | Collect Requirements | 2 | Project management plan | Input | Planning | 6 | Broader | Scope management plan
72 | 5.2 | Collect Requirements | 0 | Requirements management plan | Input | Planning | 6 | Incorporated into | Project management plan
73 | 5.2 | Collect Requirements | 0 | Stakeholder management plan | Input | Planning | 6 | Incorporated into | Project management plan
74 | 5.2 | Collect Requirements | 1 | Project charter | Input | Planning | 6 | No
75 | 5.2 | Collect Requirements | 3 | Project documents | Input | Planning | 6 | Incorporated into | Stakeholder register
75 | 5.2 | Collect Requirements | 4 | Business documents | Input | Planning | 6 | Added
75 | 5.2 | Collect Requirements | 5 | Agreements | Input | Planning | 6 | Added
75 | 5.2 | Collect Requirements | 6 | Enterprise environmental factors | Input | Planning | 6 | Added
75 | 5.2 | Collect Requirements | 7 | Organizational process assets | Input | Planning | 6 | Added
76 | 5.2 | Collect Requirements | 1 | Expert judgement | Tools | Planning | 6 | Added
76 | 5.2 | Collect Requirements | 2 | Data gathering | Tools | Planning | 6 | Broader | Interviews
77 | 5.2 | Collect Requirements | 0 | Focus groups | Tools | Planning | 6 | Incorporated into | Data gathering
78 | 5.2 | Collect Requirements | 0 | Facilitated workshops | Tools | Planning | 6 | Removed
79 | 5.2 | Collect Requirements | 0 | Group creativity techniques | Tools | Planning | 6 | Removed
80 | 5.2 | Collect Requirements | 4 | Decision making | Tools | Planning | 6 | Broader | Group decision-making techniques
80 | 5.2 | Collect Requirements | 5 | Communication | Tools | Planning | 6 | Added
81 | 5.2 | Collect Requirements | 0 | Questionnaires and surveys | Tools | Planning | 6 | Incorporated into | Data gathering
82 | 5.2 | Collect Requirements | 6 | Interpersonal and team skills | Tools | Planning | 6 | Broader | Observations
83 | 5.2 | Collect Requirements | 8 | Prototypes | Tools | Planning | 6 | No
84 | 5.2 | Collect Requirements | 0 | Benchmarking | Tools | Planning | 6 | Incorporated into | Data gathering
85 | 5.2 | Collect Requirements | 7 | Context diagrams | Tools | Planning | 6 | No
86 | 5.2 | Collect Requirements | 3 | Data analysis | Tools | Planning | 6 | Broader | Document analysis
87 | 5.2 | Collect Requirements | 1 | Requirements documentation | Output | Planning | 6 | No
88 | 5.2 | Collect Requirements | 2 | Requirements traceability matrix | Output | Planning | 6 | No
89 | 5.3 | Define Scope | 2 | Project management plan | Input | Planning | 6 | Broader | Scope management plan
90 | 5.3 | Define Scope | 1 | Project charter | Input | Planning | 6 | No
91 | 5.3 | Define Scope | 3 | Project documents | Input | Planning | 6 | Broader | Requirements documentation
91 | 5.3 | Define Scope | 4 | Enterprise environmental factors | Input | Planning | 6 | Added
92 | 5.3 | Define Scope | 5 | Organizational process assets | Input | Planning | 6 | No
93 | 5.3 | Define Scope | 1 | Expert judgement | Tools | Planning | 6 | No
94 | 5.3 | Define Scope | 4 | Product analysis | Tools | Planning | 6 | No
95 | 5.3 | Define Scope | 2 | Decision making | Tools | Planning | 6 | Broader | Alternatives generation
96 | 5.3 | Define Scope | 3 | Interpersonal and team skills | Tools | Planning | 6 | Broader | Facilitated workshops
97 | 5.3 | Define Scope | 1 | Project scope statement | Output | Planning | 6 | No
98 | 5.3 | Define Scope | 2 | Project documents updates | Output | Planning | 6 | No
99 | 5.4 | Create WBS | 1 | Project management plan | Input | Planning | 6 | Broader | Scope management plan
100 | 5.4 | Create WBS | 2 | Project documents | Input | Planning | 6 | Broader | Project scope statement
101 | 5.4 | Create WBS | 0 | Requirements documentation | Input | Planning | 6 | Incorporated into | Project documents
102 | 5.4 | Create WBS | 3 | Enterprise environmental factors | Input | Planning | 6 | No
103 | 5.4 | Create WBS | 4 | Organizational process assets | Input | Planning | 6 | No
104 | 5.4 | Create WBS | 2 | Decomposition | Tools | Planning | 6 | No
105 | 5.4 | Create WBS | 1 | Expert judgement | Tools | Planning | 6 | No
106 | 5.4 | Create WBS | 1 | Scope baseline | Output | Planning | 6 | No
107 | 5.4 | Create WBS | 2 | Project documents updates | Output | Planning | 6 | No
108 | 5.5 | Validate Scope | 1 | Project management plan | Input | Controling | 6 | No
109 | 5.5 | Validate Scope | 2 | Project documents | Input | Controling | 6 | Broader | Requirements documentation
110 | 5.5 | Validate Scope | 0 | Requirements traceability matrix | Input | Controling | 6 | Incorporated into | Project documents
111 | 5.5 | Validate Scope | 3 | Verified deliverables | Input | Controling | 6 | No
112 | 5.5 | Validate Scope | 4 | Work performance data | Input | Controling | 6 | No
113 | 5.5 | Validate Scope | 1 | Inspection | Tools | Controling | 6 | No
114 | 5.5 | Validate Scope | 2 | Decision making | Tools | Controling | 6 | Broader | Group decision-making techniques
115 | 5.5 | Validate Scope | 1 | Accepted deliverables | Output | Controling | 6 | No
116 | 5.5 | Validate Scope | 3 | Change requests | Output | Controling | 6 | No
117 | 5.5 | Validate Scope | 2 | Work performance information | Output | Controling | 6 | No
118 | 5.5 | Validate Scope | 4 | Project documents updates | Output | Controling | 6 | No
119 | 5.6 | Control Scope | 1 | Project management plan | Input | Controling | 6 | No
120 | 5.6 | Control Scope | 3 | Work performance data | Input | Controling | 6 | No
121 | 5.6 | Control Scope | 2 | Project documents | Input | Controling | 6 | Broader | Requirements documentation
122 | 5.6 | Control Scope | 0 | Requirements traceability matrix | Input | Controling | 6 | Incorporated into | Project documents
123 | 5.6 | Control Scope | 4 | Organizational process assets | Input | Controling | 6 | No
124 | 5.6 | Control Scope | 1 | Data analysis | Tools | Controling | 6 | Broader | Variance analysis
125 | 5.6 | Control Scope | 1 | Work performance information | Output | Controling | 6 | No
126 | 5.6 | Control Scope | 0 | Organizational process assets updates | Output | Controling | 6 | Removed
127 | 5.6 | Control Scope | 2 | Change requests | Output | Controling | 6 | No
128 | 5.6 | Control Scope | 3 | Project management plan updates | Output | Controling | 6 | No
129 | 5.6 | Control Scope | 4 | Project documents updates | Output | Controling | 6 | No
130 | 6.1 | Plan Schedule Management | 2 | Project management plan | Input | Planning | 6 | No
131 | 6.1 | Plan Schedule Management | 1 | Project charter | Input | Planning | 6 | No
132 | 6.1 | Plan Schedule Management | 3 | Enterprise environmental factors | Input | Planning | 6 | No
133 | 6.1 | Plan Schedule Management | 4 | Organizational process assets | Input | Planning | 6 | No
134 | 6.1 | Plan Schedule Management | 1 | Expert judgement | Tools | Planning | 6 | No
135 | 6.1 | Plan Schedule Management | 2 | Data analysis | Tools | Planning | 6 | Broader | Analytical techniques
136 | 6.1 | Plan Schedule Management | 3 | Meetings | Tools | Planning | 6 | No
137 | 6.1 | Plan Schedule Management | 1 | Schedule management plan | Output | Planning | 6 | No
138 | 6.2 | Define Activities | 1 | Project management plan | Input | Planning | 6 | Broader | Schedule management plan
139 | 6.2 | Define Activities | 0 | Scope baseline | Input | Planning | 6 | Incorporated into | Project management plan
140 | 6.2 | Define Activities | 2 | Enterprise environmental factors | Input | Planning | 6 | No
141 | 6.2 | Define Activities | 3 | Organizational process assets | Input | Planning | 6 | No
142 | 6.2 | Define Activities | 2 | Decomposition | Tools | Planning | 6 | No
143 | 6.2 | Define Activities | 3 | Rolling wave planning | Tools | Planning | 6 | No
144 | 6.2 | Define Activities | 1 | Expert judgement | Tools | Planning | 6 | No
144 | 6.2 | Define Activities | 4 | Meetings | Tools | Planning | 6 | Added
145 | 6.2 | Define Activities | 1 | Activity list | Output | Planning | 6 | No
146 | 6.2 | Define Activities | 2 | Activity attributes | Output | Planning | 6 | No
147 | 6.2 | Define Activities | 3 | Milestone list | Output | Planning | 6 | No
147 | 6.2 | Define Activities | 4 | Change requests | Output | Planning | 6 | Added
147 | 6.2 | Define Activities | 5 | Project Management Plan updates | Output | Planning | 6 | Added
148 | 6.3 | Sequence Activities | 1 | Project management plan | Input | Planning | 6 | Broader | Schedule management plan
149 | 6.3 | Sequence Activities | 2 | Project documents | Input | Planning | 6 | Broader | Activity list
150 | 6.3 | Sequence Activities | 0 | Activity attributes | Input | Planning | 6 | Incorporated into | Project documents
151 | 6.3 | Sequence Activities | 0 | Milestone list | Input | Planning | 6 | Incorporated into | Project documents
152 | 6.3 | Sequence Activities | 0 | Project scope statement | Input | Planning | 6 | Incorporated into | Project management plan
153 | 6.3 | Sequence Activities | 3 | Enterprise environmental factors | Input | Planning | 6 | No
154 | 6.3 | Sequence Activities | 4 | Organizational process assets | Input | Planning | 6 | No
155 | 6.3 | Sequence Activities | 1 | Precedence diagramming method (PDM) | Tools | Planning | 6 | No
156 | 6.3 | Sequence Activities | 2 | Dependency determination | Tools | Planning | 6 | No
157 | 6.3 | Sequence Activities | 3 | Leads and lags | Tools | Planning | 6 | No
158 | 6.3 | Sequence Activities | 1 | Project schedule network diagrams | Output | Planning | 6 | No
159 | 6.3 | Sequence Activities | 2 | Project documents updates | Output | Planning | 6 | No
176 | 6.4 | Estimate Activity Durations | 1 | Project management plan | Input | Planning | 6 | Broader | Schedule management plan
177 | 6.4 | Estimate Activity Durations | 2 | Project documents | Input | Planning | 6 | Broader | Activity list
178 | 6.4 | Estimate Activity Durations | 0 | Activity attributes | Input | Planning | 6 | Incorporated into | Project documents
179 | 6.4 | Estimate Activity Durations | 0 | Resource requirements | Input | Planning | 6 | Incorporated into | Project documents
180 | 6.4 | Estimate Activity Durations | 0 | Resource calendars | Input | Planning | 6 | Incorporated into | Project documents
181 | 6.4 | Estimate Activity Durations | 0 | Project scope statement | Input | Planning | 6 | Incorporated into | Project management plan
182 | 6.4 | Estimate Activity Durations | 0 | Risk register | Input | Planning | 6 | Incorporated into | Project documents
183 | 6.4 | Estimate Activity Durations | 0 | Resource breakdown structure | Input | Planning | 6 | Removed
184 | 6.4 | Estimate Activity Durations | 3 | Enterprise environmental factors | Input | Planning | 6 | No
185 | 6.4 | Estimate Activity Durations | 4 | Organizational process assets | Input | Planning | 6 | No
186 | 6.4 | Estimate Activity Durations | 1 | Expert judgement | Tools | Planning | 6 | No
187 | 6.4 | Estimate Activity Durations | 2 | Analogous estimating | Tools | Planning | 6 | No
188 | 6.4 | Estimate Activity Durations | 3 | Parametric estimating | Tools | Planning | 6 | No
189 | 6.4 | Estimate Activity Durations | 4 | Three-point estimating | Tools | Planning | 6 | No
190 | 6.4 | Estimate Activity Durations | 0 | Group decision-making techniques | Tools | Planning | 6 | Removed
190 | 6.4 | Estimate Activity Durations | 5 | Bottom-up estimating | Tools | Planning | 6 | Added
191 | 6.4 | Estimate Activity Durations | 6 | Data analysis | Tools | Planning | 6 | Broader | Reserve analysis
191 | 6.4 | Estimate Activity Durations | 7 | Decision making | Tools | Planning | 6 | Added
191 | 6.4 | Estimate Activity Durations | 8 | Meetings | Tools | Planning | 6 | Added
192 | 6.4 | Estimate Activity Durations | 1 | Duration estimates | Output | Planning | 6 | Name change | Activity duration estimates
192 | 6.4 | Estimate Activity Durations | 2 | Basis of estimates | Output | Planning | 6 | Added
193 | 6.4 | Estimate Activity Durations | 3 | Project documents updates | Output | Planning | 6 | No
194 | 6.5 | Develop Schedule | 1 | Project management plan | Input | Planning | 6 | Broader | Schedule management plan
195 | 6.5 | Develop Schedule | 2 | Project documents | Input | Planning | 6 | Broader | Activity list
196 | 6.5 | Develop Schedule | 0 | Activity attributes | Input | Planning | 6 | Incorporated into | Project documents
197 | 6.5 | Develop Schedule | 0 | Project schedule network diagrams | Input | Planning | 6 | Incorporated into | Project documents
198 | 6.5 | Develop Schedule | 0 | Resource requirements | Input | Planning | 6 | Incorporated into | Project documents
199 | 6.5 | Develop Schedule | 0 | Resource calendars | Input | Planning | 6 | Incorporated into | Project documents
200 | 6.5 | Develop Schedule | 0 | Duration estimates | Input | Planning | 6 | Incorporated into | Project documents
201 | 6.5 | Develop Schedule | 0 | Project scope statement | Input | Planning | 6 | Incorporated into | Project management plan
202 | 6.5 | Develop Schedule | 0 | Risk register | Input | Planning | 6 | Incorporated into | Project documents
203 | 6.5 | Develop Schedule | 0 | Project team assignments | Input | Planning | 6 | Incorporated into | Project documents
204 | 6.5 | Develop Schedule | 0 | Resource breakdown structure | Input | Planning | 6 | Removed
204 | 6.5 | Develop Schedule | 3 | Agreements | Input | Planning | 6 | Added
205 | 6.5 | Develop Schedule | 4 | Enterprise environmental factors | Input | Planning | 6 | No
206 | 6.5 | Develop Schedule | 5 | Organizational process assets | Input | Planning | 6 | No
207 | 6.5 | Develop Schedule | 1 | Schedule network analysis | Tools | Planning | 6 | No
208 | 6.5 | Develop Schedule | 2 | Critical path method | Tools | Planning | 6 | No
209 | 6.5 | Develop Schedule | 0 | Critical chain method | Tools | Planning | 6 | Removed
210 | 6.5 | Develop Schedule | 3 | Resource optimization | Tools | Planning | 6 | No
211 | 6.5 | Develop Schedule | 4 | Data analysis | Tools | Planning | 6 | Broader | Modeling techniques
212 | 6.5 | Develop Schedule | 5 | Leads and lags | Tools | Planning | 6 | No
213 | 6.5 | Develop Schedule | 6 | Schedule compression | Tools | Planning | 6 | No
214 | 6.5 | Develop Schedule | 7 | Project management information system | Tools | Planning | 6 | Name change | Scheduling tool
214 | 6.5 | Develop Schedule | 8 | Agile Release Planning | Tools | Planning | 6 | Added
215 | 6.5 | Develop Schedule | 1 | Schedule baseline | Output | Planning | 6 | No
216 | 6.5 | Develop Schedule | 2 | Project schedule | Output | Planning | 6 | No
217 | 6.5 | Develop Schedule | 3 | Schedule data | Output | Planning | 6 | No
218 | 6.5 | Develop Schedule | 4 | Project calendars | Output | Planning | 6 | No
218 | 6.5 | Develop Schedule | 5 | Change requests | Output | Planning | 6 | Added
219 | 6.5 | Develop Schedule | 6 | Project management plan updates | Output | Planning | 6 | No
220 | 6.5 | Develop Schedule | 7 | Project documents updates | Output | Planning | 6 | No
221 | 6.6 | Control Schedule | 1 | Project management plan | Input | Controling | 6 | No
222 | 6.6 | Control Schedule | 2 | Project documents | Input | Controling | 6 | Broader | Project schedule
223 | 6.6 | Control Schedule | 3 | Work performance data | Input | Controling | 6 | No
224 | 6.6 | Control Schedule | 0 | Project calendars | Input | Controling | 6 | Incorporated into | Project documents
225 | 6.6 | Control Schedule | 0 | Schedule data | Input | Controling | 6 | Incorporated into | Project documents
226 | 6.6 | Control Schedule | 4 | Organizational process assets | Input | Controling | 6 | No
227 | 6.6 | Control Schedule | 1 | Data analysis | Tools | Controling | 6 | Broader | Performance reviews
227 | 6.6 | Control Schedule | 2 | Critical path method | Tools | Controling | 6 | Added
228 | 6.6 | Control Schedule | 3 | Project management information system | Tools | Controling | 6 | Name change | Project management software
229 | 6.6 | Control Schedule | 4 | Resource optimization | Tools | Controling | 6 | No
230 | 6.6 | Control Schedule | 0 | Modeling techniques | Tools | Controling | 6 | Incorporated into | Data Analysis
231 | 6.6 | Control Schedule | 5 | Leads and lags | Tools | Controling | 6 | No
232 | 6.6 | Control Schedule | 6 | Schedule compression | Tools | Controling | 6 | No
233 | 6.6 | Control Schedule | 0 | Scheduling tool | Tools | Controling | 6 | Removed
234 | 6.6 | Control Schedule | 1 | Work performance information | Output | Controling | 6 | No
235 | 6.6 | Control Schedule | 2 | Schedule forecasts | Output | Controling | 6 | No
236 | 6.6 | Control Schedule | 3 | Change requests | Output | Controling | 6 | No
237 | 6.6 | Control Schedule | 4 | Project management plan updates | Output | Controling | 6 | No
238 | 6.6 | Control Schedule | 5 | Project documents updates | Output | Controling | 6 | No
239 | 6.6 | Control Schedule | 0 | Organizational process assets updates | Output | Controling | 6 | Removed
240 | 7.1 | Plan Cost Management | 2 | Project management plan | Input | Planning | 6 | No
241 | 7.1 | Plan Cost Management | 1 | Project charter | Input | Planning | 6 | No
242 | 7.1 | Plan Cost Management | 3 | Enterprise environmental factors | Input | Planning | 6 | No
243 | 7.1 | Plan Cost Management | 4 | Organizational process assets | Input | Planning | 6 | No
244 | 7.1 | Plan Cost Management | 1 | Expert judgement | Tools | Planning | 6 | No
245 | 7.1 | Plan Cost Management | 2 | Data analysis | Tools | Planning | 6 | Broader | Analytical techniques
246 | 7.1 | Plan Cost Management | 3 | Meetings | Tools | Planning | 6 | No
247 | 7.1 | Plan Cost Management | 1 | Cost management plan | Output | Planning | 6 | No
248 | 7.2 | Estimate Costs | 1 | Project management plan | Input | Planning | 6 | Broader | Cost management plan
249 | 7.2 | Estimate Costs | 0 | Human resource management plan | Input | Planning | 6 | Incorporated into | Project management plan
250 | 7.2 | Estimate Costs | 0 | Scope baseline | Input | Planning | 6 | Incorporated into | Project management plan
251 | 7.2 | Estimate Costs | 2 | Project documents | Input | Planning | 6 | Broader | Project schedule
252 | 7.2 | Estimate Costs | 0 | Risk register | Input | Planning | 6 | Incorporated into
253 | 7.2 | Estimate Costs | 3 | Enterprise environmental factors | Input | Planning | 6 | No
254 | 7.2 | Estimate Costs | 4 | Organizational process assets | Input | Planning | 6 | No
255 | 7.2 | Estimate Costs | 1 | Expert judgement | Tools | Planning | 6 | No
256 | 7.2 | Estimate Costs | 2 | Analogous estimating | Tools | Planning | 6 | No
257 | 7.2 | Estimate Costs | 3 | Parametric estimating | Tools | Planning | 6 | No
258 | 7.2 | Estimate Costs | 4 | Bottom-up estimating | Tools | Planning | 6 | No
259 | 7.2 | Estimate Costs | 5 | Three-point estimating | Tools | Planning | 6 | No
260 | 7.2 | Estimate Costs | 6 | Data analysis | Tools | Planning | 6 | Broader | Reserve analysis
261 | 7.2 | Estimate Costs | 0 | Cost of quality | Tools | Planning | 6 | Incorporated into | Data Analysis
262 | 7.2 | Estimate Costs | 7 | Project management information system | Tools | Planning | 6 | Name change | Project management software
263 | 7.2 | Estimate Costs | 0 | Vendor bid analysis | Tools | Planning | 6 | Removed
264 | 7.2 | Estimate Costs | 8 | Decision making | Tools | Planning | 6 | Name change | Group decision-making techniques
265 | 7.2 | Estimate Costs | 1 | Cost estimates | Output | Planning | 6 | Name change | Activity cost estimates
266 | 7.2 | Estimate Costs | 2 | Basis of estimates | Output | Planning | 6 | No
267 | 7.2 | Estimate Costs | 3 | Project documents updates | Output | Planning | 6 | No
268 | 7.3 | Determine Budget | 1 | Project management plan | Input | Planning | 6 | Broader | Cost management plan
269 | 7.3 | Determine Budget | 0 | Scope baseline | Input | Planning | 6 | Incorporated into | Project management plan
270 | 7.3 | Determine Budget | 2 | Project documents | Input | Planning | 6 | Broader | Activity cost estimates
271 | 7.3 | Determine Budget | 0 | Basis of estimates | Input | Planning | 6 | Incorporated into | Project documents
272 | 7.3 | Determine Budget | 0 | Project schedule | Input | Planning | 6 | Incorporated into | Project documents
273 | 7.3 | Determine Budget | 0 | Resource calendars | Input | Planning | 6 | Incorporated into | Project documents
274 | 7.3 | Determine Budget | 0 | Risk register | Input | Planning | 6 | Incorporated into | Project documents
275 | 7.3 | Determine Budget | 4 | Agreements | Input | Planning | 6 | No
276 | 7.3 | Determine Budget | 6 | Organizational process assets | Input | Planning | 6 | No
| 7.3 | Determine Budget | 3 | Business documents | Input | Planning | 6 | Added
| 7.3 | Determine Budget | 5 | Enterprise environmental factors | Input | Planning | 6 | Added
277 | 7.3 | Determine Budget | 2 | Cost aggregation | Tools | Planning | 6 | No
278 | 7.3 | Determine Budget | 3 | Data analysis | Tools | Planning | 6 | Broader | Reserve analysis
279 | 7.3 | Determine Budget | 1 | Expert judgement | Tools | Planning | 6 | No
280 | 7.3 | Determine Budget | 4 | Historical relationships | Tools | Planning | 6 | No
281 | 7.3 | Determine Budget | 5 | Funding limit reconciliation | Tools | Planning | 6 | No
| 7.3 | Determine Budget | 6 | Financing | Tools | Planning | 6 | Added
282 | 7.3 | Determine Budget | 1 | Cost baseline | Output | Planning | 6 | No
283 | 7.3 | Determine Budget | 2 | Project funding requirements | Output | Planning | 6 | No
284 | 7.3 | Determine Budget | 3 | Project documents updates | Output | Planning | 6 | No
285 | 7.4 | Control Costs | 1 | Project management plan | Input | Controling | 6 | No
286 | 7.4 | Control Costs | 3 | Project funding requirements | Input | Controling | 6 | No
287 | 7.4 | Control Costs | 4 | Work performance data | Input | Controling | 6 | No
288 | 7.4 | Control Costs | 5 | Organizational process assets | Input | Controling | 6 | No
| 7.4 | Control Costs | 2 | Project documents | Input | Controling | 6 | Added
289 | 7.4 | Control Costs | 2 | Data analysis | Tools | Controling | 6 | Broader | Earned value management
290 | 7.4 | Control Costs | 1 | Expert judgement | Tools | Controling | 6 | Broader | Forecasting
291 | 7.4 | Control Costs | 3 | To-complete performance index (TCPI) | Tools | Controling | 6 | No
292 | 7.4 | Control Costs | 0 | Performance reviews | Tools | Controling | 6 | Removed
293 | 7.4 | Control Costs | 4 | Project management information system | Tools | Controling | 6 | Name change | Project management software
294 | 7.4 | Control Costs | 0 | Reserve analysis | Tools | Controling | 6 | Incorporated into | Data Analysis
295 | 7.4 | Control Costs | 1 | Work performance information | Output | Controling | 6 | No
296 | 7.4 | Control Costs | 2 | Cost forecasts | Output | Controling | 6 | No
297 | 7.4 | Control Costs | 3 | Change requests | Output | Controling | 6 | No
298 | 7.4 | Control Costs | 4 | Project management plan updates | Output | Controling | 6 | No
299 | 7.4 | Control Costs | 5 | Project documents updates | Output | Controling | 6 | No
300 | 7.4 | Control Costs | 0 | Organizational process assets updates | Output | Controling | 6 | Removed
301 | 8.1 | Plan Quality Management | 1 | Project charter | Input | Planning | 6 | Added
301 | 8.1 | Plan Quality Management | 2 | Project management plan | Input | Planning | 6 | No
302 | 8.1 | Plan Quality Management | 3 | Project documents | Input | Planning | 6 | Broader | Stakeholder register
303 | 8.1 | Plan Quality Management | 0 | Risk register | Input | Planning | 6 | Incorporated into | Project documents
304 | 8.1 | Plan Quality Management | 0 | Requirements documentation | Input | Planning | 6 | Incorporated into | Project documents
305 | 8.1 | Plan Quality Management | 4 | Enterprise environmental factors | Input | Planning | 6 | No
306 | 8.1 | Plan Quality Management | 5 | Organizational process assets | Input | Planning | 6 | No
307 | 8.1 | Plan Quality Management | 1 | Expert judgement | Tools | Planning | 6 | Added
307 | 8.1 | Plan Quality Management | 2 | Data gathering | Tools | Planning | 6 | Added
307 | 8.1 | Plan Quality Management | 3 | Data analysis | Tools | Planning | 6 | Added
307 | 8.1 | Plan Quality Management | 4 | Decision making | Tools | Planning | 6 | Added
307 | 8.1 | Plan Quality Management | 5 | Communication | Tools | Planning | 6 | Added
307 | 8.1 | Plan Quality Management | 6 | Test and inspection plan | Tools | Planning | 6 | Added
307 | 8.1 | Plan Quality Management | 0 | Cost-benefit analysis | Tools | Planning | 6 | Incorporated into | Data Analysis
308 | 8.1 | Plan Quality Management | 0 | Cost of quality | Tools | Planning | 6 | Incorporated into | Data Analysis
309 | 8.1 | Plan Quality Management | 0 | Seven basic quality tools | Tools | Planning | 6 | Removed
310 | 8.1 | Plan Quality Management | 0 | Benchmarking | Tools | Planning | 6 | Incorporated into | Data gathering
311 | 8.1 | Plan Quality Management | 0 | Design of experiments | Tools | Planning | 6 | Removed
312 | 8.1 | Plan Quality Management | 0 | Statistical sampling | Tools | Planning | 6 | Removed
313 | 8.1 | Plan Quality Management | 0 | Additional quality planning tools | Tools | Planning | 6 | Removed
314 | 8.1 | Plan Quality Management | 7 | Meetings | Tools | Planning | 6 | No
315 | 8.1 | Plan Quality Management | 1 | Quality management plan | Output | Planning | 6 | No
316 | 8.1 | Plan Quality Management | 0 | Process improvement plan | Output | Planning | 6 | Removed
317 | 8.1 | Plan Quality Management | 2 | Quality metrics | Output | Planning | 6 | No
319 | 8.1 | Plan Quality Management | 3 | Project management plan updates | Output | Planning | 6 | Added
318 | 8.1 | Plan Quality Management | 0 | Quality checklists | Output | Planning | 6 | Removed
319 | 8.1 | Plan Quality Management | 4 | Project documents updates | Output | Planning | 6 | No
320 | 8.2 | Manage Quality | 1 | Project management plan | Input | Executing | 6 | Broader | Quality management plan
321 | 8.2 | Manage Quality | 0 | Process improvement plan | Input | Executing | 6 | Removed
322 | 8.2 | Manage Quality | 0 | Quality metrics | Input | Executing | 6 | Incorporated into | Project documents
323 | 8.2 | Manage Quality | 0 | Quality control measurements | Input | Executing | 6 | Incorporated into | Project documents
324 | 8.2 | Manage Quality | 2 | Project documents | Input | Executing | 6 | No
324 | 8.2 | Manage Quality | 3 | Organizational process assets | Input | Executing | 6 | Added
325 | 8.2 | Manage Quality | 1 | Data gathering | Tools | Executing | 6 | Added
325 | 8.2 | Manage Quality | 3 | Decision making | Tools | Executing | 6 | Added
325 | 8.2 | Manage Quality | 4 | Communication | Tools | Executing | 6 | Added
325 | 8.2 | Manage Quality | 6 | Design for X | Tools | Executing | 6 | Added
325 | 8.2 | Manage Quality | 7 | Problem solving | Tools | Executing | 6 | Removed
326 | 8.2 | Manage Quality | 5 | Audits | Tools | Executing | 6 | Name change | Quality audits
326 | 8.2 | Manage Quality | 8 | Quality improvement methods | Tools | Executing | 6 | Added
327 | 8.2 | Manage Quality | 2 | Data analysis | Tools | Executing | 6 | Incorporated into | Process analysis
328 | 8.2 | Manage Quality | 3 | Change requests | Output | Executing | 6 | No
329 | 8.2 | Manage Quality | 4 | Project management plan updates | Output | Executing | 6 | No
330 | 8.2 | Manage Quality | 5 | Project documents updates | Output | Executing | 6 | No
331 | 8.2 | Manage Quality | 0 | Organizational process assets updates | Output | Executing | 6 | Removed
332 | 8.3 | Control Quality | 1 | Project management plan | Input | Controling | 6 | No
333 | 8.3 | Control Quality | 0 | Quality metrics | Input | Controling | 6 | Incorporated into | Project documents
334 | 8.3 | Control Quality | 0 | Quality checklists | Input | Controling | 6 | Incorporated into | Project documents
335 | 8.3 | Control Quality | 5 | Work performance data | Input | Controling | 6 | No
336 | 8.3 | Control Quality | 3 | Approved change requests | Input | Controling | 6 | No
337 | 8.3 | Control Quality | 4 | Deliverables | Input | Controling | 6 | No
338 | 8.3 | Control Quality | 2 | Project documents | Input | Controling | 6 | No
338 | 8.3 | Control Quality | 6 | Enterprise environmental factors | Input | Controling | 6 | Added
339 | 8.3 | Control Quality | 7 | Organizational process assets | Input | Controling | 6 | No
340 | 8.3 | Control Quality | 0 | Seven basic quality tools | Tools | Controling | 6 | Removed
341 | 8.3 | Control Quality | 1 | Data gathering | Tools | Controling | 6 | Broader | Statistical sampling
341 | 8.3 | Control Quality | 2 | Data analysis | Tools | Controling | 6 | Added
341 | 8.3 | Control Quality | 4 | Testing/product evalutions | Tools | Controling | 6 | Added
341 | 8.3 | Control Quality | 5 | Communication | Tools | Controling | 6 | Added
342 | 8.3 | Control Quality | 3 | Inspection | Tools | Controling | 6 | No
343 | 8.3 | Control Quality | 0 | Approved change requests review | Tools | Controling | 6 | Removed
343 | 8.3 | Control Quality | 6 | Meetings | Tools | Controling | 6 | Added
344 | 8.3 | Control Quality | 1 | Quality control measurements | Output | Controling | 6 | No
345 | 8.3 | Control Quality | 0 | Validated changes | Output | Controling | 6 | Removed
346 | 8.3 | Control Quality | 2 | Verified deliverables | Output | Controling | 6 | No
347 | 8.3 | Control Quality | 3 | Work performance information | Output | Controling | 6 | No
348 | 8.3 | Control Quality | 4 | Change requests | Output | Controling | 6 | No
349 | 8.3 | Control Quality | 5 | Project management plan updates | Output | Controling | 6 | No
350 | 8.3 | Control Quality | 6 | Project documents updates | Output | Controling | 6 | No
351 | 8.3 | Control Quality | 0 | Organizational process assets updates | Output | Controling | 6 | Removed
352 | 9.1 | Plan Resource Management | 1 | Project charter | Input | Planning | 6 | Added
352 | 9.1 | Plan Resource Management | 2 | Project management plan | Input | Planning | 6 | No
353 | 9.1 | Plan Resource Management | 3 | Project documents | Input | Planning | 6 | Broader | Activity resource requirements
354 | 9.1 | Plan Resource Management | 4 | Enterprise environmental factors | Input | Planning | 6 | No
355 | 9.1 | Plan Resource Management | 5 | Organizational process assets | Input | Planning | 6 | No
356 | 9.1 | Plan Resource Management | 2 | Communication | Tools | Planning | 6 | Broader | Organization charts and position descriptions
357 | 9.1 | Plan Resource Management | 0 | Networking | Tools | Planning | 6 | Removed
358 | 9.1 | Plan Resource Management | 3 | Organizational theory | Tools | Planning | 6 | No
359 | 9.1 | Plan Resource Management | 1 | Expert judgement | Tools | Planning | 6 | No
360 | 9.1 | Plan Resource Management | 4 | Meetings | Tools | Planning | 6 | No
361 | 9.1 | Plan Resource Management | 1 | Resource management plan | Output | Planning | 6 | Name change | Human resource management plan
160 | 9.2 | Estimate Activity Resourse | 1 | Project management plan | Input | Planning | 6 | Broader | Schedule management plan
161 | 9.2 | Estimate Activity Resourse | 2 | Project documents | Input | Planning | 6 | Broader | Activity list
162 | 9.2 | Estimate Activity Resourse | 0 | Activity attributes | Input | Planning | 6 | Incorporated into | Project documents
163 | 9.2 | Estimate Activity Resourse | 0 | Resource calendars | Input | Planning | 6 | Incorporated into | Project documents
164 | 9.2 | Estimate Activity Resourse | 0 | Risk register | Input | Planning | 6 | Incorporated into | Project documents
165 | 9.2 | Estimate Activity Resourse | 0 | Activity cost estimates | Input | Planning | 6 | Incorporated into | Project documents
166 | 9.2 | Estimate Activity Resourse | 3 | Enterprise environmental factors | Input | Planning | 6 | No
167 | 9.2 | Estimate Activity Resourse | 4 | Organizational process assets | Input | Planning | 6 | No
168 | 9.2 | Estimate Activity Resourse | 1 | Expert judgement | Tools | Planning | 6 | No
169 | 9.2 | Estimate Activity Resourse | 5 | Data analysis | Tools | Planning | 6 | Broader | Alternative analysis
169 | 9.2 | Estimate Activity Resourse | 4 | Parametric estimating | Tools | Planning | 6 | Added
170 | 9.2 | Estimate Activity Resourse | 3 | Analogous estimating | Tools | Planning | 6 | Broader | Published estimating data
171 | 9.2 | Estimate Activity Resourse | 2 | Bottom-up estimating | Tools | Planning | 6 | No
172 | 9.2 | Estimate Activity Resourse | 6 | Project management information system | Tools | Planning | 6 | Name change | Project management software
172 | 9.2 | Estimate Activity Resourse | 7 | Meetings | Tools | Planning | 6 | Added
173 | 9.2 | Estimate Activity Resourse | 1 | Resource requirements | Output | Planning | 6 | Name change | Activity resource requirements
173 | 9.2 | Estimate Activity Resourse | 2 | Basis of estimates | Output | Planning | 6 | Added
174 | 9.2 | Estimate Activity Resourse | 3 | Resource breakdown structure | Output | Planning | 6 | No
175 | 9.2 | Estimate Activity Resourse | 4 | Project documents updates | Output | Planning | 6 | No
362 | 9.3 | Acquire Resources | 1 | Project management plan | Input | Executing | 6 | Broader | Human resource management plan
362 | 9.3 | Acquire Resources | 2 | Project documents | Input | Executing | 6 | Added
363 | 9.3 | Acquire Resources | 3 | Enterprise environmental factors | Input | Executing | 6 | No
364 | 9.3 | Acquire Resources | 4 | Organizational process assets | Input | Executing | 6 | No
365 | 9.3 | Acquire Resources | 3 | Pre-assignment | Tools | Executing | 6 | No
366 | 9.3 | Acquire Resources | 2 | Interpersonal and team skills | Tools | Executing | 6 | Broader | Negotiation
367 | 9.3 | Acquire Resources | 0 | Acquisition | Tools | Executing | 6 | Removed
368 | 9.3 | Acquire Resources | 4 | Virtual teams | Tools | Executing | 6 | No
369 | 9.3 | Acquire Resources | 1 | Decision making | Tools | Executing | 6 | Broader | Multi-criteria decision analysis
370 | 9.3 | Acquire Resources | 1 | Resource assignments | Output | Executing | 6 | Name change | Project staff assignments
370 | 9.3 | Acquire Resources | 2 | Change requests | Output | Executing | 6 | Added
371 | 9.3 | Acquire Resources | 4 | Project documents updates | Output | Executing | 6 | Broader | Resource calendars
372 | 9.3 | Acquire Resources | 3 | Project management plan updates | Output | Executing | 6 | No
373 | 9.4 | Develop Team | 1 | Project management plan | Input | Executing | 6 | Broader | Human resource management plan
374 | 9.4 | Develop Team | 2 | Project documents | Input | Executing | 6 | Broader | Project staff assignments
375 | 9.4 | Develop Team | 0 | Resource calendars | Input | Executing | 6 | Incorporated into | Project documents
375 | 9.4 | Develop Team | 3 | Enterprise environmental factors | Input | Executing | 6 | Added
375 | 9.4 | Develop Team | 4 | Organizational process assets | Input | Executing | 6 | Added
376 | 9.4 | Develop Team | 3 | Interpersonal and team skills | Tools | Executing | 6 | Broader | Interpersonal skills
377 | 9.4 | Develop Team | 5 | Training | Tools | Executing | 6 | No
378 | 9.4 | Develop Team | 0 | Team-building activities | Tools | Executing | 6 | Incorporated into | Interpersonal and team skills
379 | 9.4 | Develop Team | 0 | Ground rules | Tools | Executing | 6 | Removed
380 | 9.4 | Develop Team | 1 | Colocation/Virtual teams | Tools | Executing | 6 | Broader | Colocation
380 | 9.4 | Develop Team | 2 | Communication technology | Tools | Executing | 6 | Added
381 | 9.4 | Develop Team | 4 | Recognition and rewards | Tools | Executing | 6 | No
382 | 9.4 | Develop Team | 6 | Individual and team assessments | Tools | Executing | 6 | Name change | Personnel assessment tools
382 | 9.4 | Develop Team | 7 | Meetings | Tools | Executing | 6 | Added
383 | 9.4 | Develop Team | 1 | Team performance assessments | Output | Executing | 6 | No
383 | 9.4 | Develop Team | 2 | Change requests | Output | Executing | 6 | Added
383 | 9.4 | Develop Team | 3 | Project management plan updates | Output | Executing | 6 | Added
383 | 9.4 | Develop Team | 4 | Project documents updates | Output | Executing | 6 | Added
384 | 9.4 | Develop Team | 5 | Enterprise environmental factors updates | Output | Executing | 6 | No
383 | 9.4 | Develop Team | 6 | Organizational process assets updates | Output | Executing | 6 | Added
385 | 9.5 | Manage Team | 1 | Project management plan | Input | Executing | 6 | Broader | Human resource management plan
386 | 9.5 | Manage Team | 2 | Project documents | Input | Executing | 6 | Broader | Project staff assignments
387 | 9.5 | Manage Team | 4 | Team performance assessments | Input | Executing | 6 | No
388 | 9.5 | Manage Team | 0 | Issue log | Input | Executing | 6 | Incorporated into | Project documents
389 | 9.5 | Manage Team | 3 | Work performance reports | Input | Executing | 6 | No
389 | 9.5 | Manage Team | 5 | Enterprise environmental factors | Input | Executing | 6 | Added
390 | 9.5 | Manage Team | 6 | Organizational process assets | Input | Executing | 6 | No
391 | 9.5 | Manage Team | 0 | Observation and conversation | Tools | Executing | 6 | Removed
392 | 9.5 | Manage Team | 0 | Project performance appraisals | Tools | Executing | 6 | Removed
393 | 9.5 | Manage Team | 1 | Interpersonal and team skills | Tools | Executing | 6 | Broader | Conflict management
394 | 9.5 | Manage Team | 0 | Interpersonal skills | Tools | Executing | 6 | Incorporated into | Interpersonal and team skills
394 | 9.5 | Manage Team | 2 | Project management information system | Tools | Executing | 6 | Added
395 | 9.5 | Manage Team | 1 | Change requests | Output | Executing | 6 | No
396 | 9.5 | Manage Team | 2 | Project management plan updates | Output | Executing | 6 | No
397 | 9.5 | Manage Team | 3 | Project documents updates | Output | Executing | 6 | No
398 | 9.5 | Manage Team | 4 | Enterprise environmental factors updates | Output | Executing | 6 | No
399 | 9.5 | Manage Team | 0 | Organizational process assets updates | Output | Executing | 6 | Removed
| 9.6 | Control Resources | 1 | Project management plan | Input | Controling | 6
| 9.6 | Control Resources | 2 | Project documents | Input | Controling | 6
| 9.6 | Control Resources | 3 | Work performance data | Input | Controling | 6
| 9.6 | Control Resources | 4 | Agreements | Input | Controling | 6
| 9.6 | Control Resources | 5 | Organizational process assets | Input | Controling | 6
| 9.6 | Control Resources | 1 | Data analysis | Tools | Controling | 6
| 9.6 | Control Resources | 2 | Problem solving | Tools | Controling | 6
| 9.6 | Control Resources | 3 | Interpersonal and team skills | Tools | Controling | 6
| 9.6 | Control Resources | 4 | Project management information system | Tools | Controling | 6
| 9.6 | Control Resources | 1 | Work performance information | Output | Controling | 6
| 9.6 | Control Resources | 2 | Resources allocations updates | Output | Controling | 6
| 9.6 | Control Resources | 3 | Change requests | Output | Controling | 6
| 9.6 | Control Resources | 4 | Project management plan updates | Output | Controling | 6
| 9.6 | Control Resources | 5 | Project documents updates | Output | Controling | 6
400 | 10.1 | Plan Communications Management | 1 | Project charter | Input | Planning | 6 | Added
400 | 10.1 | Plan Communications Management | 2 | Project management plan | Input | Planning | 6 | No
401 | 10.1 | Plan Communications Management | 3 | Project documents | Input | Planning | 6 | Broader | Stakeholder register
402 | 10.1 | Plan Communications Management | 4 | Enterprise environmental factors | Input | Planning | 6 | No
403 | 10.1 | Plan Communications Management | 5 | Organizational process assets | Input | Planning | 6 | No
404 | 10.1 | Plan Communications Management | 1 | Expert judgement | Tools | Planning | 6 | Added
404 | 10.1 | Plan Communications Management | 2 | Communication requirements analysis | Tools | Planning | 6 | No
405 | 10.1 | Plan Communications Management | 3 | Communication technology | Tools | Planning | 6 | No
406 | 10.1 | Plan Communications Management | 4 | Communication models | Tools | Planning | 6 | No
407 | 10.1 | Plan Communications Management | 5 | Communication methods | Tools | Planning | 6 | No
407 | 10.1 | Plan Communications Management | 6 | Interpersonal and team skills | Tools | Planning | 6 | Added
407 | 10.1 | Plan Communications Management | 7 | Data analysis | Tools | Planning | 6 | Added
408 | 10.1 | Plan Communications Management | 8 | Meetings | Tools | Planning | 6 | No
409 | 10.1 | Plan Communications Management | 1 | Communications management plan | Output | Planning | 6 | No
410 | 10.1 | Plan Communications Management | 2 | Project management plan updates | Output | Planning | 6 | Added
410 | 10.1 | Plan Communications Management | 3 | Project documents updates | Output | Planning | 6 | No
411 | 10.2 | Manage Communications | 1 | Project management plan | Input | Executing | 6 | Broader | Communications management plan
411 | 10.2 | Manage Communications | 2 | Project documents | Input | Executing | 6 | Added
412 | 10.2 | Manage Communications | 3 | Work performance reports | Input | Executing | 6 | No
413 | 10.2 | Manage Communications | 4 | Enterprise environmental factors | Input | Executing | 6 | No
414 | 10.2 | Manage Communications | 5 | Organizational process assets | Input | Executing | 6 | No
415 | 10.2 | Manage Communications | 1 | Communication technology | Tools | Executing | 6 | No
416 | 10.2 | Manage Communications | 0 | Communication models | Tools | Executing | 6 | Removed
417 | 10.2 | Manage Communications | 2 | Communication methods | Tools | Executing | 6 | No
417 | 10.2 | Manage Communications | 3 | Communication skills | Tools | Executing | 6 | Added
418 | 10.2 | Manage Communications | 4 | Project management information system | Tools | Executing | 6 | Name change | Information management systems
419 | 10.2 | Manage Communications | 5 | Performance reporting | Tools | Executing | 6 | No
419 | 10.2 | Manage Communications | 6 | Interpersonal and team skills | Tools | Executing | 6 | Added
419 | 10.2 | Manage Communications | 7 | Meetings | Tools | Executing | 6 | Added
420 | 10.2 | Manage Communications | 1 | Project communications | Output | Executing | 6 | No
421 | 10.2 | Manage Communications | 2 | Project management plan updates | Output | Executing | 6 | No
422 | 10.2 | Manage Communications | 3 | Project documents updates | Output | Executing | 6 | No
423 | 10.2 | Manage Communications | 4 | Organizational process assets updates | Output | Executing | 6 | No
424 | 10.3 | Monitor Communications | 1 | Project management plan | Input | Controling | 6 | No
425 | 10.3 | Monitor Communications | 2 | Project documents | Input | Controling | 6 | Broader | Project communications
426 | 10.3 | Monitor Communications | 0 | Issue log | Input | Controling | 6 | Incorporated into | Project documents
427 | 10.3 | Monitor Communications | 3 | Work performance data | Input | Controling | 6 | No
427 | 10.3 | Monitor Communications | 4 | Enterprise environmental factors | Input | Controling | 6 | Added
428 | 10.3 | Monitor Communications | 5 | Organizational process assets | Input | Controling | 6 | No
429 | 10.3 | Monitor Communications | 2 | Project management information system | Tools | Controling | 6 | Name change | Information management systems
430 | 10.3 | Monitor Communications | 1 | Expert judgement | Tools | Controling | 6 | No
430 | 10.3 | Monitor Communications | 3 | Data analysis | Tools | Controling | 6 | Added
430 | 10.3 | Monitor Communications | 4 | Interpersonal and team skills | Tools | Controling | 6 | Added
431 | 10.3 | Monitor Communications | 5 | Meetings | Tools | Controling | 6 | No
432 | 10.3 | Monitor Communications | 1 | Work performance information | Output | Controling | 6 | No
433 | 10.3 | Monitor Communications | 2 | Change requests | Output | Controling | 6 | No
434 | 10.3 | Monitor Communications | 3 | Project management plan updates | Output | Controling | 6 | No
435 | 10.3 | Monitor Communications | 4 | Project documents updates | Output | Controling | 6 | No
436 | 10.3 | Monitor Communications | 0 | Organizational process assets updates | Output | Controling | 6 | Removed
437 | 11.1 | Plan Risk Management | 2 | Project management plan | Input | Planning | 6 | No
438 | 11.1 | Plan Risk Management | 1 | Project charter | Input | Planning | 6 | No
439 | 11.1 | Plan Risk Management | 3 | Project documents | Input | Planning | 6 | Broader | Stakeholder register
440 | 11.1 | Plan Risk Management | 4 | Enterprise environmental factors | Input | Planning | 6 | No
441 | 11.1 | Plan Risk Management | 5 | Organizational process assets | Input | Planning | 6 | No
442 | 11.1 | Plan Risk Management | 2 | Data analysis | Tools | Planning | 6 | Broader | Analytical techniques
443 | 11.1 | Plan Risk Management | 1 | Expert judgement | Tools | Planning | 6 | No
444 | 11.1 | Plan Risk Management | 3 | Meetings | Tools | Planning | 6 | No
445 | 11.1 | Plan Risk Management | 1 | Risk management plan | Output | Planning | 6 | No
446 | 11.2 | Identify Risks | 1 | Project management plan | Input | Planning | 6 | Broader | Risk management plan
447 | 11.2 | Identify Risks | 0 | Cost management plan | Input | Planning | 6 | Incorporated into | Project management plan
448 | 11.2 | Identify Risks | 0 | Schedule management plan | Input | Planning | 6 | Incorporated into | Project management plan
449 | 11.2 | Identify Risks | 0 | Quality management plan | Input | Planning | 6 | Incorporated into | Project management plan
450 | 11.2 | Identify Risks | 0 | Human resource management plan | Input | Planning | 6 | Incorporated into | Project management plan
451 | 11.2 | Identify Risks | 0 | Scope baseline | Input | Planning | 6 | Incorporated into | Project management plan
452 | 11.2 | Identify Risks | 0 | Activity cost estimates | Input | Planning | 6 | Incorporated into | Project documents
453 | 11.2 | Identify Risks | 0 | Activity duration estimates | Input | Planning | 6 | Incorporated into | Project documents
454 | 11.2 | Identify Risks | 0 | Stakeholder register | Input | Planning | 6 | Incorporated into | Project documents
455 | 11.2 | Identify Risks | 1 | Project documents | Input | Planning | 6 | No
456 | 11.2 | Identify Risks | 4 | Procurement documentation | Input | Planning | 6 | Name change | Procurement documents
457 | 11.2 | Identify Risks | 5 | Enterprise environmental factors | Input | Planning | 6 | No
458 | 11.2 | Identify Risks | 6 | Organizational process assets | Input | Planning | 6 | No
459 | 11.2 | Identify Risks | 3 | Data analysis | Tools | Planning | 6 | Broader | Documentation reviews
460 | 11.2 | Identify Risks | 2 | Data gathering | Tools | Planning | 6 | Name change | Information gathering techniques
461 | 11.2 | Identify Risks | 0 | Checklist analysis | Tools | Planning | 6 | Incorporated into | Data gathering
462 | 11.2 | Identify Risks | 0 | Assumptions analysis | Tools | Planning | 6 | Incorporated into | Data Analysis
463 | 11.2 | Identify Risks | 0 | Diagramming techniques | Tools | Planning | 6 | Incorporated into | Data Analysis
464 | 11.2 | Identify Risks | 0 | SWOT analysis | Tools | Planning | 6 | Incorporated into | Data Analysis
465 | 11.2 | Identify Risks | 1 | Expert judgement | Tools | Planning | 6 | No
465 | 11.2 | Identify Risks | 4 | Interpersonal and team skills | Tools | Planning | 6 | Added
465 | 11.2 | Identify Risks | 5 | Prompt lists | Tools | Planning | 6 | Added
465 | 11.2 | Identify Risks | 6 | Meetings | Tools | Planning | 6 | Added
466 | 11.2 | Identify Risks | 1 | Risk register | Output | Planning | 6 | No
466 | 11.2 | Identify Risks | 2 | Risk report | Output | Planning | 6 | Added
466 | 11.2 | Identify Risks | 3 | Project documents updates | Output | Planning | 6 | Added
467 | 11.3 | Perform Qualitative Risk Analysis | 1 | Project management plan | Input | Planning | 6 | Broader | Risk management plan
468 | 11.3 | Perform Qualitative Risk Analysis | 0 | Scope baseline | Input | Planning | 6 | Incorporated into | Project management plan
469 | 11.3 | Perform Qualitative Risk Analysis | 2 | Project documents | Input | Planning | 6 | Broader | Risk register
470 | 11.3 | Perform Qualitative Risk Analysis | 3 | Enterprise environmental factors | Input | Planning | 6 | No
471 | 11.3 | Perform Qualitative Risk Analysis | 4 | Organizational process assets | Input | Planning | 6 | No
472 | 11.3 | Perform Qualitative Risk Analysis | 3 | Data analysis | Tools | Planning | 6 | Broader | Risk probability and impact assessment
473 | 11.3 | Perform Qualitative Risk Analysis | 6 | Communication | Tools | Planning | 6 | Broader | Probability and impact matrix
474 | 11.3 | Perform Qualitative Risk Analysis | 0 | Risk data quality assessment | Tools | Planning | 6 | Incorporated into | Data Analysis
475 | 11.3 | Perform Qualitative Risk Analysis | 5 | Risk categorization | Tools | Planning | 6 | No
476 | 11.3 | Perform Qualitative Risk Analysis | 0 | Risk urgency assessment | Tools | Planning | 6 | Incorporated into | Data Analysis
477 | 11.3 | Perform Qualitative Risk Analysis | 1 | Expert judgement | Tools | Planning | 6 | No
477 | 11.3 | Perform Qualitative Risk Analysis | 2 | Data gathering | Tools | Planning | 6 | Added
477 | 11.3 | Perform Qualitative Risk Analysis | 4 | Interpersonal and team skills | Tools | Planning | 6 | Added
478 | 11.3 | Perform Qualitative Risk Analysis | 1 | Project documents updates | Output | Planning | 6 | No
479 | 11.4 | Perform Quantitative Risk Analysis | 1 | Project management plan | Input | Planning | 6 | Broader | Risk management plan
480 | 11.4 | Perform Quantitative Risk Analysis | 0 | Cost management plan | Input | Planning | 6 | Incorporated into | Project management plan
481 | 11.4 | Perform Quantitative Risk Analysis | 0 | Schedule management plan | Input | Planning | 6 | Incorporated into | Project management plan
482 | 11.4 | Perform Quantitative Risk Analysis | 2 | Project documents | Input | Planning | 6 | Broader | Risk register
483 | 11.4 | Perform Quantitative Risk Analysis | 3 | Enterprise environmental factors | Input | Planning | 6 | No
484 | 11.4 | Perform Quantitative Risk Analysis | 4 | Organizational process assets | Input | Planning | 6 | No
485 | 11.4 | Perform Quantitative Risk Analysis | 2 | Data gathering | Tools | Planning | 6 | Name change | Data gathering and representation techniques
486 | 11.4 | Perform Quantitative Risk Analysis | 4 | Representations of uncertainty | Tools | Planning | 6 | Broader | Quantitative risk analysis and modeling techniques
487 | 11.4 | Perform Quantitative Risk Analysis | 1 | Expert judgement | Tools | Planning | 6 | No
487 | 11.4 | Perform Quantitative Risk Analysis | 3 | Interpersonal and team skills | Tools | Planning | 6 | Added
487 | 11.4 | Perform Quantitative Risk Analysis | 5 | Data analysis | Tools | Planning | 6 | Added
488 | 11.4 | Perform Quantitative Risk Analysis | 1 | Project documents updates | Output | Planning | 6 | No
489 | 11.5 | Plan Risk Responses | 1 | Project management plan | Input | Planning | 6 | Broader | Risk management plan
490 | 11.5 | Plan Risk Responses | 2 | Project documents | Input | Planning | 6 | Broader | Risk register
490 | 11.5 | Plan Risk Responses | 3 | Enterprise environmental factors | Input | Planning | 6 | Added
490 | 11.5 | Plan Risk Responses | 4 | Organizational process assets | Input | Planning | 6 | Added
491 | 11.5 | Plan Risk Responses | 4 | Strategies for threats | Tools | Planning | 6 | Name change | Strategies for negative risks or threats
492 | 11.5 | Plan Risk Responses | 5 | Strategies for opportunities | Tools | Planning | 6 | Name change | Strategies for positive risks or opportunities
493 | 11.5 | Plan Risk Responses | 6 | Contingent response strategies | Tools | Planning | 6 | No
494 | 11.5 | Plan Risk Responses | 1 | Expert judgement | Tools | Planning | 6 | No
494 | 11.5 | Plan Risk Responses | 2 | Data gathering | Tools | Planning | 6 | Added
494 | 11.5 | Plan Risk Responses | 3 | Interpersonal and team skills | Tools | Planning | 6 | Added
494 | 11.5 | Plan Risk Responses | 7 | Strategies for overall project risks | Tools | Planning | 6 | Added
494 | 11.5 | Plan Risk Responses | 8 | Decision making | Tools | Planning | 6 | Added
495 | 11.5 | Plan Risk Responses | 1 | Change requests | Output | Planning | 6 | Added
495 | 11.5 | Plan Risk Responses | 2 | Project management plan updates | Output | Planning | 6 | No
496 | 11.5 | Plan Risk Responses | 3 | Project documents updates | Output | Planning | 6 | No
| 11.6 | Implement Risk Responses | 1 | Project management plan | Input | Executing | 6
| 11.6 | Implement Risk Responses | 2 | Project documents | Input | Executing | 6
| 11.6 | Implement Risk Responses | 3 | Enterprise environmental factors | Input | Executing | 6
| 11.6 | Implement Risk Responses | 1 | Expert judgement | Tools | Executing | 6
| 11.6 | Implement Risk Responses | 2 | Resource allocation | Tools | Executing | 6
| 11.6 | Implement Risk Responses | 3 | Interpersonal and team skills | Tools | Executing | 6
| 11.6 | Implement Risk Responses | 4 | Project management information system | Tools | Executing | 6
| 11.6 | Implement Risk Responses | 1 | Change requests | Output | Executing | 6
| 11.6 | Implement Risk Responses | 2 | Project documents updates | Output | Executing | 6
497 | 11.6 | Monitor Risks | 1 | Project management plan | Input | Controling | 6 | No
498 | 11.6 | Monitor Risks | 2 | Project documents | Input | Controling | 6 | Broader | Risk register
499 | 11.6 | Monitor Risks | 3 | Work performance data | Input | Controling | 6 | No
500 | 11.6 | Monitor Risks | 4 | Work performance reports | Input | Controling | 6 | No
501 | 11.6 | Monitor Risks | 0 | Risk reassessment | Tools | Controling | 6 | Removed
502 | 11.6 | Monitor Risks | 0 | Risk audits | Tools | Controling | 6 | Removed
503 | 11.6 | Monitor Risks | 0 | Variance and trend analysis | Tools | Controling | 6 | Incorporated into | Data Analysis
504 | 11.6 | Monitor Risks | 0 | Technical performance measurement | Tools | Controling | 6 | Incorporated into | Data Analysis
505 | 11.6 | Monitor Risks | 1 | Data analysis | Tools | Controling | 6 | Broader | Reserve analysis
506 | 11.6 | Monitor Risks | 2 | Meetings | Tools | Controling | 6 | No
507 | 11.6 | Monitor Risks | 1 | Work performance information | Output | Controling | 6 | No
508 | 11.6 | Monitor Risks | 2 | Change requests | Output | Controling | 6 | No
509 | 11.6 | Monitor Risks | 3 | Project management plan updates | Output | Controling | 6 | No
510 | 11.6 | Monitor Risks | 4 | Project documents updates | Output | Controling | 6 | No
511 | 11.6 | Monitor Risks | 5 | Organizational process assets updates | Output | Controling | 6 | No
511 | 12.1 | Plan Procurement Management | 1 | Project charter | Input | Planning | 6 | Added
511 | 12.1 | Plan Procurement Management | 2 | Business documents | Input | Planning | 6 | Added
512 | 12.1 | Plan Procurement Management | 0 | Scope baseline | Input | Planning | 6 | Incorporated into | Project management plan
513 | 12.1 | Plan Procurement Management | 3 | Project management plan | Input | Planning | 6 | No
514 | 12.1 | Plan Procurement Management | 4 | Project documents | Input | Planning | 6 | Broader | Requirements documentation
515 | 12.1 | Plan Procurement Management | 0 | Risk register | Input | Planning | 6 | Incorporated into | Project documents
516 | 12.1 | Plan Procurement Management | 0 | Activity resource requirements | Input | Planning | 6 | Incorporated into | Project documents
517 | 12.1 | Plan Procurement Management | 0 | Project schedule | Input | Planning | 6 | Incorporated into | Project documents
518 | 12.1 | Plan Procurement Management | 0 | Activity cost estimates | Input | Planning | 6 | Incorporated into | Project documents
519 | 12.1 | Plan Procurement Management | 0 | Stakeholder register | Input | Planning | 6 | Incorporated into | Project documents
520 | 12.1 | Plan Procurement Management | 5 | Enterprise environmental factors | Input | Planning | 6 | No
521 | 12.1 | Plan Procurement Management | 6 | Organizational process assets | Input | Planning | 6 | No
522 | 12.1 | Plan Procurement Management | 3 | Data analysis | Tools | Planning | 6 | Broader | Make-or-buy analysis
523 | 12.1 | Plan Procurement Management | 1 | Expert judgement | Tools | Planning | 6 | No
524 | 12.1 | Plan Procurement Management | 2 | Data gathering | Tools | Planning | 6 | Broader | Market research
524 | 12.1 | Plan Procurement Management | 4 | Source selection analysis | Tools | Planning | 6 | Added
525 | 12.1 | Plan Procurement Management | 5 | Meetings | Tools | Planning | 6 | No
526 | 12.1 | Plan Procurement Management | 1 | Procurement management plan | Output | Planning | 6 | No
526 | 12.1 | Plan Procurement Management | 2 | Procurement strategy | Output | Planning | 6 | Added
527 | 12.1 | Plan Procurement Management | 4 | Procurement statement of work | Output | Planning | 6 | No
528 | 12.1 | Plan Procurement Management | 3 | Bid documents | Output | Planning | 6 | Name change | Procurement documents
529 | 12.1 | Plan Procurement Management | 5 | Source selection criteria | Output | Planning | 6 | No
530 | 12.1 | Plan Procurement Management | 6 | Make-or-buy decisions | Output | Planning | 6 | No
530 | 12.1 | Plan Procurement Management | 7 | Independent cost estimates | Output | Planning | 6 | Added
531 | 12.1 | Plan Procurement Management | 8 | Change requests | Output | Planning | 6 | No
532 | 12.1 | Plan Procurement Management | 9 | Project documents updates | Output | Planning | 6 | No
533 | 12.2 | Conduct Procurements | 1 | Project management plan | Input | Executing | 6 | Broader | Procurement management plan
534 | 12.2 | Conduct Procurements | 3 | Procurement documentation | Input | Executing | 6 | Name change | Procurement documents
535 | 12.2 | Conduct Procurements | 0 | Source selection criteria | Input | Executing | 6 | Incorporated into
536 | 12.2 | Conduct Procurements | 4 | Seller proposals | Input | Executing | 6 | No
537 | 12.2 | Conduct Procurements | 2 | Project documents | Input | Executing | 6 | No
538 | 12.2 | Conduct Procurements | 0 | Make-or-buy decisions | Input | Executing | 6 | Incorporated into
539 | 12.2 | Conduct Procurements | 0 | Procurement statement of work | Input | Executing | 6 | Incorporated into
540 | 12.2 | Conduct Procurements | 5 | Enterprise environmental factors | Input | Executing | 6 | Added
540 | 12.2 | Conduct Procurements | 6 | Organizational process assets | Input | Executing | 6 | No
541 | 12.2 | Conduct Procurements | 3 | Bidder conferences | Tools | Executing | 6 | Name change | Bidder conference
542 | 12.2 | Conduct Procurements | 0 | Proposal evaluation techniques | Tools | Executing | 6 | Removed
543 | 12.2 | Conduct Procurements | 0 | Independent estimates | Tools | Executing | 6 | Removed
544 | 12.2 | Conduct Procurements | 1 | Expert judgement | Tools | Executing | 6 | No
545 | 12.2 | Conduct Procurements | 2 | Advertising | Tools | Executing | 6 | No
546 | 12.2 | Conduct Procurements | 4 | Data analysis | Tools | Executing | 6 | Broader | Analytical techniques
547 | 12.2 | Conduct Procurements | 5 | Negotiation | Tools | Executing | 6 | Name change | Procurement negotiations
548 | 12.2 | Conduct Procurements | 1 | Selected sellers | Output | Executing | 6 | No
549 | 12.2 | Conduct Procurements | 2 | Agreements | Output | Executing | 6 | No
550 | 12.2 | Conduct Procurements | 0 | Resource calendars | Output | Executing | 6 | Removed
551 | 12.2 | Conduct Procurements | 3 | Change requests | Output | Executing | 6 | No
552 | 12.2 | Conduct Procurements | 4 | Project management plan updates | Output | Executing | 6 | No
553 | 12.2 | Conduct Procurements | 5 | Project documents updates | Output | Executing | 6 | No
553 | 12.2 | Conduct Procurements | 6 | Organizational process assets updates | Output | Executing | 6 | Added
554 | 12.3 | Control Procurements | 1 | Project management plan | Input | Controling | 6 | No
555 | 12.3 | Control Procurements | 4 | Procurement documentation | Input | Controling | 6 | Name change | Procurement documents
556 | 12.3 | Control Procurements | 3 | Agreements | Input | Controling | 6 | No
556 | 12.3 | Control Procurements | 2 | Project documents | Input | Controling | 6 | Added
557 | 12.3 | Control Procurements | 5 | Approved change requests | Input | Controling | 6 | No
558 | 12.3 | Control Procurements | 0 | Work performance reports | Input | Controling | 6 | Removed
559 | 12.3 | Control Procurements | 6 | Work performance data | Input | Controling | 6 | No
559 | 12.3 | Control Procurements | 7 | Enterprise environmental factors | Input | Controling | 6 | Added
559 | 12.3 | Control Procurements | 8 | Organizational process assets | Input | Controling | 6 | Added
560 | 12.3 | Control Procurements | 1 | Expert judgement | Tools | Controling | 6 | Added
560 | 12.3 | Control Procurements | 0 | Contract change control system | Tools | Controling | 6 | Removed
561 | 12.3 | Control Procurements | 3 | Data analysis | Tools | Controling | 6 | Broader | Procurement performance reviews
562 | 12.3 | Control Procurements | 4 | Inspection | Tools | Controling | 6 | Narrower | Inspections and audits
562 | 12.3 | Control Procurements | 5 | Audits | Tools | Controling | 6 | Narrower | Inspections and audits
563 | 12.3 | Control Procurements | 0 | Performance reporting | Tools | Controling | 6 | Removed
564 | 12.3 | Control Procurements | 6 | Payment systems | Tools | Controling | 6 | No
565 | 12.3 | Control Procurements | 2 | Claims administration | Tools | Controling | 6 | No
566 | 12.3 | Control Procurements | 0 | Records management system | Tools | Controling | 6 | Removed
567 | 12.3 | Control Procurements | 1 | Closed procurements | Output | Controling | 6 | Added
567 | 12.3 | Control Procurements | 2 | Work performance information | Output | Controling | 6 | No
567 | 12.3 | Control Procurements | 3 | Procurement documentation updates | Output | Controling | 6 | Added
568 | 12.3 | Control Procurements | 4 | Change requests | Output | Controling | 6 | No
569 | 12.3 | Control Procurements | 5 | Project management plan updates | Output | Controling | 6 | No
570 | 12.3 | Control Procurements | 6 | Project documents updates | Output | Controling | 6 | No
571 | 12.3 | Control Procurements | 7 | Organizational process assets updates | Output | Controling | 6 | No
579 | 13.1 | Identify Stakeholders | 1 | Project charter | Input | Initiating | 6 | No
580 | 13.1 | Identify Stakeholders | 0 | Procurement documents | Input | Initiating | 6 | Removed
| 13.1 | Identify Stakeholders | 2 | Business documents | Input | Initiating | 6 | Added
| 13.1 | Identify Stakeholders | 3 | Project management plan | Input | Initiating | 6 | Added
| 13.1 | Identify Stakeholders | 4 | Project documents | Input | Initiating | 6 | Added
| 13.1 | Identify Stakeholders | 5 | Agreements | Input | Initiating | 6 | Added
581 | 13.1 | Identify Stakeholders | 6 | Enterprise environmental factors | Input | Initiating | 6 | No
582 | 13.1 | Identify Stakeholders | 7 | Organizational process assets | Input | Initiating | 6 | No | Stakeholder analysis
583 | 13.1 | Identify Stakeholders | 3 | Data analysis | Tools | Initiating | 6 | Broader
584 | 13.1 | Identify Stakeholders | 1 | Expert judgement | Tools | Initiating | 6 | No
585 | 13.1 | Identify Stakeholders | 4 | Meetings | Tools | Initiating | 6 | No
| 13.1 | Identify Stakeholders | 2 | Data gathering | Tools | Initiating | 6 | Added
586 | 13.1 | Identify Stakeholders | 1 | Stakeholder register | Output | Initiating | 6 | No
| 13.1 | Identify Stakeholders | 2 | Change requests | Output | Initiating | 6 | Added
| 13.1 | Identify Stakeholders | 3 | Project management plan updates | Output | Initiating | 6 | Added
| 13.1 | Identify Stakeholders | 4 | Project documents updates | Output | Initiating | 6 | Added
587 | 13.2 | Plan Stakeholder Management | 1 | Project management plan | Input | Planning | 6 | No | Stakeholder register
588 | 13.2 | Plan Stakeholder Management | 2 | Project documents | Input | Planning | 6 | Broader
| 13.2 | Plan Stakeholder Management | 3 | Agreements | Input | Planning | 6 | Added
589 | 13.2 | Plan Stakeholder Management | 4 | Enterprise environmental factors | Input | Planning | 6 | No
590 | 13.2 | Plan Stakeholder Management | 5 | Organizational process assets | Input | Planning | 6 | No
591 | 13.2 | Plan Stakeholder Management | 1 | Expert judgement | Tools | Planning | 6 | No
592 | 13.2 | Plan Stakeholder Management | 5 | Meetings | Tools | Planning | 6 | No
593 | 13.2 | Plan Stakeholder Management | 0 | Analytical techniques | Tools | Planning | 6 | Removed
| 13.2 | Plan Stakeholder Management | 2 | Data gathering | Tools | Planning | 6 | Added
| 13.2 | Plan Stakeholder Management | 3 | Data analysis | Tools | Planning | 6 | Added
| 13.2 | Plan Stakeholder Management | 4 | Decision making | Tools | Planning | 6 | Added | Stakeholder management plan
594 | 13.2 | Plan Stakeholder Management | 1 | Stakeholder engagement plan | Output | Planning | 6 | Name change
595 | 13.2 | Plan Stakeholder Management | 0 | Project documents updates | Output | Planning | 6 | Removed | Stakeholder management plan
596 | 13.3 | Manage Stakeholder Engagement | 1 | Project management plan | Input | Executing | 6 | Broader
597 | 13.3 | Manage Stakeholder Engagement | 0 | Communications management plan | Input | Executing | 6 | Broader | Change log
598 | 13.3 | Manage Stakeholder Engagement | 2 | Project documents | Input | Executing | 6 | Broader
| 13.3 | Manage Stakeholder Engagement | 3 | Enterprise environmental factors | Input | Executing | 6 | Added
599 | 13.3 | Manage Stakeholder Engagement | 4 | Organizational process assets | Input | Executing | 6 | No
| 13.3 | Manage Stakeholder Engagement | 1 | Expert judgement | Tools | Executing | 6 | Added
| 13.3 | Manage Stakeholder Engagement | 2 | Inspection | Tools | Executing | 6 | Added | Communication methods
600 | 13.3 | Manage Stakeholder Engagement | 3 | Communication | Tools | Executing | 6 | Name change | Interpersonal skills
601 | 13.3 | Manage Stakeholder Engagement | 4 | Interpersonal and team skills | Tools | Executing | 6 | Broader
602 | 13.3 | Manage Stakeholder Engagement | 0 | Management skills | Tools | Executing | 6 | Broader
| 13.3 | Manage Stakeholder Engagement | 5 | Ground rules | Tools | Executing | 6 | Added
| 13.3 | Manage Stakeholder Engagement | 6 | Meetings | Tools | Executing | 6 | Added
603 | 13.3 | Manage Stakeholder Engagement | 0 | Issue log | Output | Executing | 6 | Broader
604 | 13.3 | Manage Stakeholder Engagement | 1 | Change requests | Output | Executing | 6 | No
605 | 13.3 | Manage Stakeholder Engagement | 2 | Project management plan updates | Output | Executing | 6 | No
606 | 13.3 | Manage Stakeholder Engagement | 3 | Project documents updates | Output | Executing | 6 | No
607 | 13.3 | Manage Stakeholder Engagement | 0 | Organizational process assets updates | Output | Executing | 6 | Removed
608 | 13.4 | Control Stakeholder Engagement | 1 | Project management plan | Input | Controling | 6 | No
609 | 13.4 | Control Stakeholder Engagement | 0 | Issue log | Input | Controling | 6 | Broader
610 | 13.4 | Control Stakeholder Engagement | 3 | Work performance data | Input | Controling | 6 | No
611 | 13.4 | Control Stakeholder Engagement | 2 | Project documents | Input | Controling | 6 | No
| 13.4 | Control Stakeholder Engagement | 4 | Enterprise environmental factors | Input | Controling | 6 | Added
| 13.4 | Control Stakeholder Engagement | 5 | Organizational process assets | Input | Controling | 6 | Added
| 13.4 | Control Stakeholder Engagement | 1 | Data analysis | Tools | Controling | 6 | Added
| 13.4 | Control Stakeholder Engagement | 2 | Decision making | Tools | Controling | 6 | Added
| 13.4 | Control Stakeholder Engagement | 3 | Communication | Tools | Controling | 6 | Added
| 13.4 | Control Stakeholder Engagement | 4 | Interpersonal and team skills | Tools | Controling | 6 | Added
612 | 13.4 | Control Stakeholder Engagement | 0 | Information management systems | Tools | Controling | 6 | Removed
613 | 13.4 | Control Stakeholder Engagement | 0 | Expert judgement | Tools | Controling | 6 | Removed
614 | 13.4 | Control Stakeholder Engagement | 5 | Meetings | Tools | Controling | 6 | No
615 | 13.4 | Control Stakeholder Engagement | 1 | Work performance information | Output | Controling | 6 | No
616 | 13.4 | Control Stakeholder Engagement | 2 | Change requests | Output | Controling | 6 | No
617 | 13.4 | Control Stakeholder Engagement | 3 | Project management plan updates | Output | Controling | 6 | No
618 | 13.4 | Control Stakeholder Engagement | 4 | Project documents updates | Output | Controling | 6 | No
619 | 13.4 | Control Stakeholder Engagement | 0 | Organizational process assets updates | Output | Controling | 6 | Removed
Note on F231: Eduardo Montes: Removed Activity in the beginning
Note on F234: Eduardo Montes: staff to team

## Input-Tools-Output
Change | (All)
Row Labels | Count of Group
Input | 312
Accepted deliverables | 1
Activity attributes | 4
Activity cost estimates | 3
Activity duration estimates | 1
Activity resource requirements | 1
Agreements | 10
Approved change requests | 3
Basis of estimates | 1
Business documents | 6
Change requests | 1
Communications management plan | 1
Cost forecasts | 1
Cost management plan | 2
Deliverables | 2
Duration estimates | 1
Enterprise environmental factors | 41
Human resource management plan | 2
Issue log | 3
Make-or-buy decisions | 1
Milestone list | 1
Organizational process assets | 46
Outputs from other processes | 1
Process improvement plan | 1
Procurement documentation | 4
Procurement documents | 1
Procurement statement of work | 1
Project calendars | 1
Project charter | 13
Project documents | 43
Project funding requirements | 1
Project management plan | 47
Project schedule | 2
Project schedule network diagrams | 1
Project scope statement | 3
Project statement of work | 1
Project team assignments | 1
Quality checklists | 1
Quality control measurements | 1
Quality management plan | 1
Quality metrics | 2
Requirements documentation | 2
Requirements management plan | 1
Requirements traceability matrix | 2
Resource breakdown structure | 2
Resource calendars | 5
Resource requirements | 2
Risk register | 7
Schedule data | 1
Schedule management plan | 2
Scope baseline | 6
Seller proposals | 1
Source selection criteria | 1
Stakeholder management plan | 1
Stakeholder register | 2
Team performance assessments | 1
Validated changes | 1
Verified deliverables | 1
Work performance data | 10
Work performance information | 1
Work performance reports | 5
Output | 188
Accepted deliverables | 1
Activity attributes | 1
Activity list | 1
Agreements | 1
Approved change requests | 1
Assumption log | 1
Basis of estimates | 3
Bid documents | 1
Change log | 1
Change requests | 24
Closed procurements | 1
Communications management plan | 1
Cost baseline | 1
Cost estimates | 1
Cost forecasts | 1
Cost management plan | 1
Deliverables | 1
Duration estimates | 1
Enterprise environmental factors updates | 2
Final product, service, or result transition | 1
Independent cost estimates | 1
Issue log | 2
Lessons learned register | 1
Make-or-buy decisions | 1
Milestone list | 1
Organizational process assets updates | 17
Process improvement plan | 1
Procurement documentation updates | 1
Procurement management plan | 1
Procurement statement of work | 1
Procurement strategy | 1
Project calendars | 1
Project charter | 1
Project communications | 1
Project documents updates | 39
Project funding requirements | 1
Project management plan | 1
Project management plan updates | 26
Project schedule | 1
Project schedule network diagrams | 1
Project scope statement | 1
Quality checklists | 1
Quality control measurements | 1
Quality management plan | 1
Quality metrics | 1
Requirements documentation | 1
Requirements management plan | 1
Requirements traceability matrix | 1
Resource assignments | 1
Resource breakdown structure | 1
Resource calendars | 1
Resource management plan | 1
Resource requirements | 1
Resources allocations updates | 1
Risk management plan | 1
Risk register | 1
Risk report | 1
Schedule baseline | 1
Schedule data | 1
Schedule forecasts | 1
Schedule management plan | 1
Scope baseline | 1
Scope management plan | 1
Selected sellers | 1
Source selection criteria | 1
Stakeholder engagement plan | 1
Stakeholder register | 1
Team performance assessments | 1
Validated changes | 1
Verified deliverables | 1
Work performance data | 1
Work performance information | 10
Work performance reports | 1
Tools | 288
Acquisition | 1
Additional quality planning tools | 1
Advertising | 1
Agile Release Planning | 1
Analogous estimating | 3
Analytical techniques | 1
Approved change requests review | 1
Assumptions analysis | 1
Audits | 2
Benchmarking | 2
Bidder conferences | 1
Bottom-up estimating | 3
Change control tools | 1
Checklist analysis | 1
Claims administration | 1
Colocation/Virtual teams | 1
Communication | 8
Communication methods | 2
Communication models | 2
Communication requirements analysis | 1
Communication skills | 1
Communication technology | 3
Context diagrams | 1
Contingent response strategies | 1
Contract change control system | 1
Cost aggregation | 1
Cost of quality | 2
Cost-benefit analysis | 1
Critical chain method | 1
Critical path method | 2
Data analysis | 32
Data gathering | 13
Decision making | 13
Decomposition | 2
Dependency determination | 1
Design for X | 1
Design of experiments | 1
Diagramming techniques | 1
Expert judgement | 36
Facilitated workshops | 1
Financing | 1
Focus groups | 1
Funding limit reconciliation | 1
Ground rules | 2
Group creativity techniques | 1
Group decision-making techniques | 1
Historical relationships | 1
Independent estimates | 1
Individual and team assessments | 1
Information management | 1
Information management systems | 1
Inspection | 4
Interpersonal and team skills | 19
Interpersonal skills | 1
Knowledge management | 1
Leads and lags | 3
Management skills | 1
Meetings | 26
Modeling techniques | 1
Negotiation | 1
Networking | 1
Observation and conversation | 1
Organizational theory | 1
Parametric estimating | 3
Payment systems | 1
Performance reporting | 2
Performance reviews | 1
Pre-assignment | 1
Precedence diagramming method (PDM) | 1
Problem solving | 2
Product analysis | 1
Project management information system | 12
Project performance appraisals | 1
Prompt lists | 1
Proposal evaluation techniques | 1
Prototypes | 1
Quality improvement methods | 1
Questionnaires and surveys | 1
Recognition and rewards | 1
Records management system | 1
Representations of uncertainty | 1
Reserve analysis | 1
Resource allocation | 1
Resource optimization | 2
Risk audits | 1
Risk categorization | 1
Risk data quality assessment | 1
Risk reassessment | 1
Risk urgency assessment | 1
Rolling wave planning | 1
Schedule compression | 2
Schedule network analysis | 1
Scheduling tool | 1
Seven basic quality tools | 2
Source selection analysis | 1
Statistical sampling | 1
Strategies for opportunities | 1
Strategies for overall project risks | 1
Strategies for threats | 1
SWOT analysis | 1
Team-building activities | 1
Technical performance measurement | 1
Test and inspection plan | 1
Testing/product evalutions | 1
Three-point estimating | 2
To-complete performance index (TCPI) | 1
Training | 1
Variance and trend analysis | 1
Vendor bid analysis | 1
Virtual teams | 1
Grand Total | 788

## Param
GP | Knowledge Areas | Change |  | To Be Removed
Initiating | 4 - Integration | Added
Planning | 5 - Scope | Removed |  | 1
Executing | 6 - Time | Broader
Monitoring & Controlling | 7 - Cost | Narrower
Closing | 8 - Quality | Name change
Tools & Techniques | 9 - Human Resource | Incorporated into | Incorporated in other | 1
Management Plan | 10 - Communications
11 - Risk
12 - Procurement
13 - Stakeholder